## README
Tallyrow prioritisation workbook
Product Management Models & Measurements · Prioritisation models
Tallyrow is a fictional invoicing and payments app. Every number in this workbook is invented for teaching.
Tabs
RICE · Tallyrow: the quarter's eight backlog items, scored with honest inputs and a live ranked view.
RICE · your backlog: the same sheet, blank. Fill the grey input columns; the score, rank and ranked view update.
Weighted · Tallyrow: four criteria and weights agreed before scoring, the eight items scored 1-5, a live ranked view.
Weighted · your backlog: blank. Agree the criteria, weights and anchors, and date them, before anyone scores.
ICE · experiments: small, cheap tests scored Impact × Confidence × Ease, plus blank rows for your own.
MoSCoW · Tallyrow: the quarter fitted to 10 person-months. Musts at 60%, Should 20%, Could 20%, five Won'ts.
MoSCoW · your release: blank. Set your capacity, place every item, keep the Musts at or under about 60%.
CD3 · Tallyrow: cost of delay ÷ duration, ranked; plus the dates-first block (e-invoicing starts by week 3) and smart reminders' range.
CD3 · your top five: blank. A weekly cost of delay and a duration per item; then list any item with a date the ranking can't see.
WSJF · Tallyrow: SAFe's three cost-of-delay columns and job size on the modified Fibonacci scale, ranked.
WSJF · your backlog: blank. Score one column at a time; the smallest item in each column gets a 1.
Anchors: RICE's unit, impact scale, confidence rule and effort rule.
Every prioritisation model from the course is here. Same eight items, several rankings: compare them before you decide.
Google Sheets: File > Import > Upload, or open from Drive. Dropdowns and formulas carry over.
Sources: RICE, Sean McBride, Intercom, 5 Jan 2018. ICE, credited to Sean Ellis. MoSCoW, Dai Clegg (1994), DSDM / Agile Business Consortium. CD3, Black Swan Farming. WSJF, SAFe (Scaled Agile Framework).

## RICE · Tallyrow
RICE · Tallyrow backlog (honest inputs)
One unit, one impact anchor, one evidence rule. Change any grey input and watch the ranked view.
# | Item | Squad | Reach | Reach unit | Unit check | Impact | Confidence | Effort (p-m) | RICE score | Rank | Evidence (why this confidence?) | Rank | Ranked view | Score
1 | Payment link | Get Paid | 12000 | businesses / quarter |  | 2 | 80% | 2 |  |  | Reach: support-ticket and usage data. Impact: no measured lift yet. Effort: engineering estimate. | 1
2 | Smart reminders | Get Paid | 24000 | businesses / quarter |  | 2 | 50% | 4 |  |  | Timing model not built. Impact borrowed from a competitor's demo. Reach assumes every reminder sender adopts it. | 2
3 | Recurring invoices | Invoicing | 8000 | businesses / quarter |  | 1 | 100% | 2 |  |  | Reach: account data. Impact: top request on the feedback board. Effort: engineering estimate. | 3
4 | E-invoicing | Platform & Compliance | 3000 | businesses / quarter |  | 3 | 80% | 4 |  |  | Reach: businesses in the one market. Impact: legally required there. Effort depends on the regulator's spec. | 4
5 | Multi-currency | Invoicing | 1500 | businesses / quarter |  | 2 | 80% | 2 |  |  | Reach: one large agency deal plus a few accounts. Impact: sales input. Effort: engineering estimate. | 5
6 | Client portal | Invoicing | 15000 | businesses / quarter |  | 1 | 80% | 6 |  |  | Impact anchored to invoices paid on time: some lift, so medium. Effort: design and engineering estimate. | 6
7 | Late-fee automation | Get Paid | 6000 | businesses / quarter |  | 1 | 80% | 2 |  |  | Reach: accounts with overdue invoices. Not scored by RICE: risk to clients' relationships (guardrail). | 7
8 | Receipt capture | Invoicing | 10000 | businesses / quarter |  | 0.5 | 80% | 4 |  |  | Reach: user survey. Impact: adjacent to the core job, so low. | 8
Formula: RICE = (Reach × Impact × Confidence) ÷ Effort. Scales and rules: see the Anchors tab.
Every Tallyrow number is invented for teaching.

## RICE · your backlog
RICE · your backlog
Agree the Anchors tab first. Fill Item to Effort; write the evidence for every confidence value.
# | Item | Squad | Reach | Reach unit | Unit check | Impact | Confidence | Effort (p-m) | RICE score | Rank | Evidence (why this confidence?) | Rank | Ranked view | Score
1 | [11 empty] | 1
2 | [11 empty] | 2
3 | [11 empty] | 3
4 | [11 empty] | 4
5 | [11 empty] | 5
6 | [11 empty] | 6
7 | [11 empty] | 7
8 | [11 empty] | 8
9 | [11 empty] | 9
10 | [11 empty] | 10
11 | [11 empty] | 11
12 | [11 empty] | 12
13 | [11 empty] | 13
14 | [11 empty] | 14
15 | [11 empty] | 15
Formula: RICE = (Reach × Impact × Confidence) ÷ Effort. Scales and rules: see the Anchors tab.
Every Tallyrow number is invented for teaching.

## Weighted · Tallyrow
Weighted scoring · Tallyrow backlog
Criteria and weights agreed with Maya and Tomás before anyone scored. Change a weight and watch the ranked view.
| Criterion | Lift to invoices paid on time | Revenue and retention | Strategic or compliance need | Ease | Weights total
| Weight | 40% | 25% | 15% | 20%
| Agreed by / date | Maya (CEO), Tomás (Finance lead) |  |  | Planning day 1, before scoring
# | Item | Lift (1-5) | Revenue (1-5) | Strategic (1-5) | Ease (1-5) | Weighted total | Rank | Rank | Ranked view | Total
1 | Payment link | 5 | 4 | 3 | 4
2 | Smart reminders | 4 | 3 | 4 | 2
3 | Recurring invoices | 3 | 4 | 2 | 4
4 | E-invoicing | 1 | 3 | 5 | 2
5 | Multi-currency | 1 | 3 | 2 | 4
6 | Client portal | 3 | 2 | 2 | 1
7 | Late-fee automation | 2 | 4 | 1 | 4
8 | Receipt capture | 1 | 2 | 1 | 2
Criteria anchors: agree these with the weights, BEFORE anyone scores
| Criterion | 1 means |  |  | 5 means
| Lift | Barely moves invoices paid on time, or reaches few customers |  |  | Large lift for most of the customer base
| Revenue | No effect on revenue or on customers staying |  |  | Clear new revenue, or a top reason customers stay
| Strategic | Nice to have |  |  | Legally required, or a bet the company has stated
| Ease | 6 or more person-months (4 = about 2, 2 = about 4) |  |  | Well under 1 person-month
Weighted total = SUMPRODUCT(weights, scores). Equal totals share a rank.
Weights and anchors are agreed, written down and dated before scoring. Change them after scoring and the ranking is chosen first, justified second.
Like RICE, this tab has no column for time: deadlines are priced by Cost of Delay.
Every Tallyrow number is invented for teaching.

## Weighted · your backlog
Weighted scoring · your backlog
Step 1: criteria, weights (total 100%) and anchors, agreed and dated. Step 2: only then, score each item 1-5.
| Criterion | Lift to invoices paid on time | Revenue and retention | Strategic or compliance need | Ease | Weights total
Weight
Agreed by / date
# | Item | Lift (1-5) | Revenue (1-5) | Strategic (1-5) | Ease (1-5) | Weighted total | Rank | Rank | Ranked view | Total
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Criteria anchors: agree these with the weights, BEFORE anyone scores
| Criterion | 1 means |  |  | 5 means
Lift
Revenue
Strategic
Ease
Weighted total = SUMPRODUCT(weights, scores). Equal totals share a rank.
Weights and anchors are agreed, written down and dated before scoring. Change them after scoring and the ranking is chosen first, justified second.
Like RICE, this tab has no column for time: deadlines are priced by Cost of Delay.

## ICE · experiments
ICE · small experiments
For a pile of small, cheap tests, not roadmap bets. Impact, Confidence, Ease: 1-10 each, multiplied.
# | Experiment idea | Impact | Confidence | Ease | ICE score | Rank
1 | "Pay now" button in the reminder email | 7 | 8 | 9
2 | Reminder three days before the due date | 6 | 5 | 8
3 | Friendlier subject line | 3 | 6 | 10
4 | SMS reminders | 6 | 4 | 3
5 | Show the business its client's payment history | 4 | 3 | 5
6
7
8
9
10
11
12
13
14
15
Rows 1-5: the Get Paid squad's reminder-email ideas (Tallyrow, invented). Rows 6-15: yours.
ICE is credited to Sean Ellis. Three unanchored 1-10 guesses are easy to inflate: keep it for cheap tests.

## MoSCoW · Tallyrow
MoSCoW · Tallyrow quarter
The agreed board: every Must passed one of the four tests. Change a category and watch the bar.
| Capacity this timebox (person-months) |  | 10
# | Item | Requested by | Effort (p-m) | Category | Why · which test? | Category | Person-months | % of capacity | Bar (█ = ½ person-month) | Check
1 | Payment link | Priya (Support) | 2 | Must | No point delivering the quarter without it (getting paid) | Capacity
2 | Smart reminders | Maya (CEO) | 4 | Won't | Fails every test; untested. Full build: not this time | Must limit (~60%)
3 | Recurring invoices | Customers (top request) | 2 | Should | Most requested; painful to leave out, nothing breaks | Must
4 | E-invoicing | Aisha (Compliance) | 4 | Must | Not legal without it (one market) | Should
5 | Multi-currency | Daniel (Sales) | 2 | Won't | Release works without it. Tell Daniel now | Could
6 | Client portal | Design team | 6 | Won't | Not this time | Planned total
7 | Late-fee automation | Tomás (Finance) | 2 | Won't | Not this time | Won't (this time)
8 | Receipt capture | User survey | 4 | Won't | Not this time
9 | Reminders concierge test | Maya (CEO) | 0.5 | Could | Support times reminders by hand for volunteer businesses
10 | Reminders minimal version | Maya (CEO) | 1.5 | Could | Only if the concierge test passes. Dropped first
11
12
13
14
The four Must tests (DSDM): a Must passes at least one
| 1. No point delivering on the date without it |  |  |  | Payment link: the quarter is about getting paid
| 2. Not legal without it |  |  |  | E-invoicing: one market's legal requirement
3. Unsafe without it
4. Cannot deliver a viable solution without it
Must: the Minimum Usable SubseT the timebox guarantees to deliver.
Should: important but not vital. Painful to leave out, may need a workaround; the release still works.
Could: wanted but less important. Your contingency: the first thing dropped when a Must runs over.
Won't (this time): agreed not to be delivered in this timebox. Not rejected, not forgotten.
Musts typically no more than about 60% of the effort in the timebox; Coulds around 20%.
MoSCoW scopes a fixed timebox; it does not rank. Inside the Musts, use another model to order the work.
Source: MoSCoW, Dai Clegg (1994); DSDM, Agile Business Consortium, "MoSCoW Prioritisation".
Every Tallyrow number is invented for teaching.

## MoSCoW · your release
MoSCoW · your next release
Step 1: enter your capacity in person-months. Step 2: list every item with its effort. Step 3: place each one, then add up the Musts.
Capacity this timebox (person-months)
# | Item | Requested by | Effort (p-m) | Category | Why · which test? | Category | Person-months | % of capacity | Bar (█ = ½ person-month) | Check
1 | [5 empty] | Capacity
2 | [5 empty] | Must limit (~60%)
3 | [5 empty] | Must
4 | [5 empty] | Should
5 | [5 empty] | Could
6 | [5 empty] | Planned total
7 | [5 empty] | Won't (this time)
8
9
10
11
12
13
14
15
16
17
18
19
20
The four Must tests (DSDM): a Must passes at least one
1. No point delivering on the date without it
2. Not legal without it
3. Unsafe without it
4. Cannot deliver a viable solution without it
Must: the Minimum Usable SubseT the timebox guarantees to deliver.
Should: important but not vital. Painful to leave out, may need a workaround; the release still works.
Could: wanted but less important. Your contingency: the first thing dropped when a Must runs over.
Won't (this time): agreed not to be delivered in this timebox. Not rejected, not forgotten.
Musts typically no more than about 60% of the effort in the timebox; Coulds around 20%.
MoSCoW scopes a fixed timebox; it does not rank. Inside the Musts, use another model to order the work.
Source: MoSCoW, Dai Clegg (1994); DSDM, Agile Business Consortium, "MoSCoW Prioritisation".

## CD3 · Tallyrow
CD3 · Tallyrow backlog
Weekly cost of delay ÷ weeks of work. Then check the dates block: CD3 cannot see a deadline.
CD3 = cost of delay ÷ duration. Start with the highest.
# | Item | Urgency profile | Cost of delay ($k / week) | Duration (weeks) | CD3 | Rank | Rank | Ranked view | CD3
1 | Payment link | Long, peak unaffected | 15 | 4
2 | Smart reminders | Long, peak affected | 10 | 8
3 | Recurring invoices | Long, peak unaffected | 6 | 4
4 | E-invoicing | External deadline | 0 | 8
5 | Multi-currency | Treated as steady | 1.2 | 4
6 | Client portal | Long, peak unaffected | 3 | 12
7 | Late-fee automation | Long, peak unaffected | 4 | 4
8 | Receipt capture | Long, peak unaffected | 1 | 8
Dates first: schedule date-bound work backwards from its date, BEFORE you sort by CD3
| Date-bound item | Date (week of quarter) | Delivery (weeks) | Latest start (week) | Buffer (weeks) | Start by
| E-invoicing | 12 | 8 |  | 1
Then let CD3 order everything else around it. Today's cost of delay for a deadline item is zero, so CD3 alone puts it last.
Ranges: CD3 is only as good as the cost of delay you feed it
| Item | CoD low ($k / week) | CoD high ($k / week) | Duration (weeks) | CD3 low | CD3 high
| Smart reminders | 0 | 20 | 8
CD3: Cost of Delay Divided by Duration (Black Swan Farming). Short, urgent items go first.
Cost of delay in the same unit for every row ($ thousands per week here); duration in weeks.
Profiles and weekly figures are the cost-of-delay estimates from the urgency-profiles lesson.
Every Tallyrow number is invented for teaching.

## CD3 · your top five
CD3 · your top five
Step 1: a weekly cost of delay and a duration per item. Step 2: any item with a date goes in the dates block first.
CD3 = cost of delay ÷ duration. Start with the highest.
# | Item | Urgency profile | Cost of delay ($k / week) | Duration (weeks) | CD3 | Rank | Rank | Ranked view | CD3
1
2
3
4
5
6
7
8
9
10
Dates first: schedule date-bound work backwards from its date, BEFORE you sort by CD3
| Date-bound item | Date (week of quarter) | Delivery (weeks) | Latest start (week) | Buffer (weeks) | Start by
Then let CD3 order everything else around it. Today's cost of delay for a deadline item is zero, so CD3 alone puts it last.
Ranges: CD3 is only as good as the cost of delay you feed it
| Item | CoD low ($k / week) | CoD high ($k / week) | Duration (weeks) | CD3 low | CD3 high
CD3: Cost of Delay Divided by Duration (Black Swan Farming). Short, urgent items go first.
Cost of delay in the same unit for every row ($ thousands per week here); duration in weeks.

## WSJF · Tallyrow
WSJF · Tallyrow backlog
SAFe's Weighted Shortest Job First on the same eight items. Watch the time criticality column.
WSJF = (value + time criticality + risk / opportunity) ÷ job size
# | Item | User-business value | Time criticality | Risk reduction / opportunity enablement | Cost of delay (sum) | Job size | WSJF | Rank | Rank | Ranked view | WSJF
1 | Payment link | 13 | 8 | 3 |  | 1
2 | Smart reminders | 8 | 5 | 8 |  | 2
3 | Recurring invoices | 8 | 3 | 2 |  | 1
4 | E-invoicing | 5 | 20 | 8 |  | 2
5 | Multi-currency | 3 | 8 | 1 |  | 1
6 | Client portal | 5 | 1 | 2 |  | 3
7 | Late-fee automation | 5 | 2 | 1 |  | 1
8 | Receipt capture | 1 | 1 | 1 |  | 2
Smallest item = 1?
Modified Fibonacci scale: 1, 2, 3, 5, 8, 13, 20. Estimate ONE column at a time: the smallest item in the column gets a 1, everything else is sized against it.
User-business value: how much users or the business gain. Time criticality: how fast the value decays, or whether a date is coming.
Risk reduction / opportunity enablement: does doing it make other work safer, or possible?
Job size stands in for duration. SAFe calls it a proxy: dependencies can override the order.
Source: WSJF as defined by SAFe (Scaled Agile Framework).
Every Tallyrow number is invented for teaching.

## WSJF · your backlog
WSJF · your backlog
List the items, then fill one column at a time. In each column, the smallest item gets a 1.
WSJF = (value + time criticality + risk / opportunity) ÷ job size
# | Item | User-business value | Time criticality | Risk reduction / opportunity enablement | Cost of delay (sum) | Job size | WSJF | Rank | Rank | Ranked view | WSJF
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Smallest item = 1?
Modified Fibonacci scale: 1, 2, 3, 5, 8, 13, 20. Estimate ONE column at a time: the smallest item in the column gets a 1, everything else is sized against it.
User-business value: how much users or the business gain. Time criticality: how fast the value decays, or whether a date is coming.
Risk reduction / opportunity enablement: does doing it make other work safer, or possible?
Job size stands in for duration. SAFe calls it a proxy: dependencies can override the order.
Source: WSJF as defined by SAFe (Scaled Agile Framework).

## Anchors
Scoring anchors: agree these BEFORE anyone scores
One session, one unit, one impact anchor, one evidence rule, for every item you will compare.
Reach unit | businesses / quarter | People or events per time period. Every row uses this unit, or the scores are not comparable.
Impact anchor question |  | How much will this lift invoices paid on time, for each business it reaches?
Impact scale
massive | 3
high | 2
medium | 1
low | 0.5
minimal | 0.25
Confidence rule |  | Adapted from the worked examples in Intercom's RICE article. Write the evidence next to the number.
high | 100% | Data for reach, user research for impact, an engineering estimate for effort.
medium | 80% | Data for reach and effort, but unsure about impact.
low | 50% | Reach, impact and effort could all be off.
below 50% |  | "Total moonshot" (Intercom). Do not score it yet: run a cheap test first.
Effort | person-months | Everyone involved. Whole numbers, and 0.5 for anything well under a month.
Formula | (R × I × C) ÷ E | Total impact per time worked.
Read the result
• |  | Sort, then re-evaluate: does any score look too high or too low? Check its inputs first.
• |  | Not a hard and fast rule: dependencies and table stakes can justify a different order.
• |  | RICE has no column for time (deadlines: see Cost of Delay) or for trust (guardrails).
• |  | Never compare RICE scores across teams or sessions: different units, anchors and habits.
Source |  | Sean McBride, "RICE: Simple prioritization for product managers", Intercom, 5 Jan 2018
https://www.intercom.com/blog/rice-simple-prioritization-for-product-managers/